### 

**EE Senior Design**

**Project Statement of Work**

**Click Sensor Hub**

**Texas State University**

**Ingram School of Engineering**

**Alfonso de la Morena**

**Dylan Dean, Mohamed Sghari**

**SPONSOR NXP**

**6501 W William Cannon Dr**

**Austin, TX 78735**

**09/19/2018**

|  |  |  |  |
| --- | --- | --- | --- |
| **Revision History** | | | |
| **Version** | **Date** | **Description** | **Author** |
| 0.1 | 09/15/2018 | Add section owners | Alfonso |
| 0.2 | 09/15/2018 | First draft of my sections filled | Alfonso |
| 0.3 | 09/18/2018 | Review and edit | Alfonso |
| 0.4 | 09/18/2018 | Completed Section 5 | Dean |
| 0.5 | 09/19/2018 | Completed Section 2 | Dean |
| 0.6 | 09/19/2018 | Start Section 3 | Dean |
| 0.7 | 09/19/2018 | Continued Section 3 | Alfonso |
| 0.8 | 09/19/2018 | Finalized Section 3 | Mohamed |
| 0.9 | 09/19/2018 | Final review before signatures | Alfonso |

**Table of Contents**

[1. Executive Summary 2](#_Toc525119812)

[2. Business Need 2](#_Toc525119813)

[3. Product Scope Description 3](#_Toc525119814)

[Part A: Interface 3](#_Toc525119815)

[Part B: FRDM-KL46Z 3](#_Toc525119816)

[Part C) MikroElektronika Clicks 5](#_Toc525119817)

[4. Project Scope Description 7](#_Toc525119818)

[5. Sponsor Support Elements 9](#_Toc525119819)

[6. Approvals 10](#_Toc525119820)

# Executive Summary

Alfonso de la Morena:

The project is to work with the FRDM-KL46Z microprocessor board by NXP, create a Printed Circuit Board (PCB) that connects it to a minimum of 4 Clicks from MikroElektronika and write software that makes the board compatible with at least 10 Clicks. The purpose of the Clicks is to add functionality to Hexiwear devices by NXP by expanding their sensor capabilities. For example, one click may add a temperature sensor while another may add the capacity to detect C02 levels. The goal being that the KL46Z and similar FRDM board to have the same compatibility as the Hexiwear with the Clicks. Additionally, the data read from the freedom board needs to be easily usable. For this purpose, a website will be created that reads the information gathered by the clicks to creates graphs and other statistical representations. A set of instructions will be created to facilitate the open source use of the project for other individuals.

The applications of this product include giving the FRDM-KL46Z an easy to use platform for gathering data using the 10 Clicks that will be selected with the possibility of expanding it to more Clicks. One example could be to use the FRDM-KL46Z along with a Weather Click and a GPS Click to track information on a custom weather balloon. Another application could be to pair the FRDM-KL46Z with a SpeakUp Click and Bluetooth Click to operate a small robot vehicle with voice commands. Both applications might have been possible previously with a Hexiwear but the FRDM-KL46Z is a more capable and reliable device.

The first part of the project will focus on getting the sensors to operate properly on the FRDM-KL46Z. Once the 4-Click PCB has been implemented and the data is successfully transferred from the Clicks to a computer via the FRDM-KL46Z, the next phase of the project will begin. In the second phase, the focus will be writing the code to translate the readings on the sensors from the Clicks to a text file that will be sent to the website. The final phase will focus on the design of the website. The website must include instructions on how to implement the Clicks with the FRDM-KL46Z, as well as display any data gathered in tables, graphs and other forms of statistical representations.

# Business Need

Dylan Dean:

Currently the Hexiware device is the IoT platform of choice for NXP student projects. The application of this product in previous student projects has been limited due to the Hexiware’s lack of durability under student induced stress conditions. Also, in past projects the number of Clicks on the docking station were limited to three, either for budget reasons or device limitation.

The business goal is to provide FRDM board platforms with an easy to use modular Sensor Hub, designed to gather data using an interchangeable set of four to eight Clicks. With hopes of maintaining a price point at or below the current docking station being utilized by Hexiware. Because we will be designing the PCB an opportunity to correct pin layout issues and achieve connectivity speed and reliability on par or above the current station is a goal. Switching to the FRDM platform will solve the issue of durability and expand upon current sensor number limitations.

Extending the capabilities of the Sensor Hub, a website will be created as a powerful addition to FRDM IoT platform. The website will provide an analysis tool to display gathered data into statistical tables and models, along with technical documentation on Sensor Hub.

# Product Scope Description

Mohamed Sghari:

## Interface

The Freedom KL46Z hardware, FRDM-KL46Z, is a sophisticated platformer by NXP, that can be developed to be a useful everyday application. FRDM-KL46Z is ideal for rapid prototyping of microcontroller-based applications. The main goal of the project is to provide an easy way to use interface between the FRDM-KL46Z board and a minimum of 10 Clicks by MikroElektronika. Each of the devices specific features are discussed in Sections B and C. This section focuses more on the desired integration gained from this project.

**Features:**

* A PCB board with connectivity to a minimum of 4 Clicks (with a stretch goal of connecting 8 Clicks)
  + In stretch goal there would be a need for separate power supply
* An Mbed library with implementation for a minimum 10 Clicks to transfer sensor information that converts to a formatted text file.
* A website that integrates the data collected by the sensors and displays them in different statistical representations (e.g. a line or bar graph)

|  |  |
| --- | --- |
| **Features** | **Performance Targets** |
| PCB that connects FRDM-KL46Z with Clicks | Ability to connect 4 clicks at a time with a stretch goal of connecting 8 clicks   * Stretch goal includes an additional power supply for the PCB |
| Mbed Library | Library that implements reading from selected 10 Clicks with a stretch goal of 15 Clicks |
| Website | Website that receives the data gathered and displays it in an easy to read, statistical format   * Use of Tableau interactive data visualization software |

## B) FRDM-KL46Z

The Freedom KL46Z is an ultra-low-cost development platform enabled by the Kinetis® L series KL4x MCU family built on the Arm® Cortex®-M0+ processor. An overview of the – can be seen in Figure 1.




Figure 1.

**Features:**

* MKL46Z256VLLZ4 MCU (48 MHz, 256KB Flash, 32 KB RAM, Low power, 100LQFP package)
* Dual role USB interface with mini-B USB connector
* Open SDA
* 4-digit segment LCD module
* Capacitive touch slider
* Ambient light sensor
* MMA8451Q accelerometer
* MAG3110 Magnetometer
* 2 user LEDs
* 2 user push buttons
* Flexible power supply options – USB, coin cell battery, external source
* Battery-ready, power-measurement access points
* Easy access to MCU I/O via Arduino ™ R3 compatible I/O connectors

|  |  |
| --- | --- |
| **Features** | **Performance Targets** |
| Multi-Clock Operating Frequencies | For each mode:   * 32-40 kHz (low freq. mode) * 3-8 MHz (high freq. mode, low range) * 8-32 MHz (high freq. mode, high range) |
| USB Interface | Ability to configure as a full-speed USB device.  VREGIN must be powered to enable the internal circuitry of USB |
| Serial Port | Functional Serial Port connection for Clicks that can make use of it |
| Reset | Ability to use reset button to restart sensing capabilities |
| Debugging | Implement functional C code to troubleshoot and perform unit tests |
| Capacitive Touch Slider | Two Touch Sense Input (TSI) signals, TSI0 CH9/PTB16, and TSI0 CH10/PTB17 are connected to capacitive electrodes configured as a touch slider |
| Three-axis Accelerometer | Interfaced through an I2C bus |
| Three-axis Magnetometer | Interfaced through an I2C bus and one GPIO  signals |
| LEDs | Two LED, Green LED is PWM capable |
| Visible light sensor | Ability to sense light levels |
| Multiple inputs | 100-pin LQFP. Some pins are utilized in on-board circuitry, but many are directly connected to one of four I/O headers. |

Reference:

* <https://www.nxp.com/support/developer-resources/evaluation-and-development-boards/freedom-development-boards/mcu-boards/freedom-development-platform-for-kinetis-kl3x-and-kl4x-mcus:FRDM-KL46Z>

## C) MikroElektronika Clicks

Clicks by MikroElektronika are devices originally meant to amplify the sensor capabilities of devices that are compatabile with the mikroBUS standard. The mikroBUS™ socket comprises a pair of 1×8 female headers with a proprietary pin configuration and silkscreen markings. The pinout (always laid out in the same order) consists of three groups of communications pins (SPI, UART and I2C), six additional pins (PWM, Interrupt, Analog input, Reset and Chip select), and two power groups (+3.3V and 5V). The layout of the mikroBUS standard chip can be seen in Figure 2.




Figure 2.

The following list of features provides the 10 selected Clicks that will be made compatible with the Freedom KL46Z for the scope of the project.

|  |  |  |
| --- | --- | --- |
| **Features** | **Performance Targets** | **Price** |
| [Temp&Hum 2 Click](https://www.mikroe.com/temphum-2-click) | Measures a wide range of temperature and relative humidity values with a great accuracy   * 1.8 V Power supply * I2C interface | $16.00 |
| [Weather Click](https://www.mikroe.com/weather-click) | Detects humidity, pressure, and temperature   * 3.3V Power supply * SPI or I2C interface | $22.00 |
| [Color 5 click](https://www.mikroe.com/color-5-click) | Integrated color sensing device   * 3.3V and 5V Power supply * I2C interface | $16.00 |
| [BarGraph 2 Click](https://www.mikroe.com/bargraph-2-click) | 10-segment bar graph display click, which uses a high-quality, multicolor bar graph LED display   * 3.3V Power supply * PWM or SPI interface | $19.00 |
| [Accel 5 click](https://www.mikroe.com/accel-5-click) | Triaxial accelerometer sensor   * 3.3V Power supply * I2C or SPI interface | $19.00 |
| [Gaussmeter click](https://www.mikroe.com/gaussmeter-click) | Gaussmeter click is a device that is used for measuring the magnetic field in X, Y and Z axes   * 3.3V Power supply * I2C or SPI interface | $19.00 |
| [LightRanger 3 Click](https://www.mikroe.com/lightranger-3-click) | Accurate distance measurement based on a ToF (Time of Flight) measurement principle   * 3.3 V Power supply * I2C interface | $24.00 |
| [Alcohol Click](https://www.mikroe.com/alcohol-click) | Portable alcohol detector, breathalyzer for estimating BAC   * 3.3V Power supply * Analog | $15.00 |
| [Air Quality Click](https://www.mikroe.com/air-quality-click) | detecting a variety of gases that impact air quality in homes and offices   * 3.3V Power supply * Analog | $16.50 |
| [microSD click](https://www.mikroe.com/microsd-click?search_query=sd+card+click&results=6) | A microSD card slot for microSD cards used as a mass storage media for portable devices   * 3.3 V Power supply * SPI interface | $16.00 |
| [Slider click](https://www.mikroe.com/slider-click) | A mechanical slide action potentiometer   * 3.3V or 5V Power supply * GPIO or SPI interface | $24.00 |

Reference:

* <https://www.mikroe.com/click>
* <https://www.mikroe.com/mikrobus>

# Project Scope Description

Alfonso de la Morena:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project Schedule – Fall 2018** | | | | |
| **Task** | **DRI** | **Duration, Wks** | **Start** | **End** |
| Define Project Scope   * Approval by Sponsor * Approval by Instructor | Alfonso | 2 | 09/01/18 | 09/12/18 |
| Research   * $30 Budget for each teammate for educational tools on subject | Alfonso | 36 | 09/01/18 | 05/01/18 |
| Hardcopy Statement of Work | Alfonso | 2 | 09/10/18 | 09/24/18 |
| Hardcopy Functional Spec | Alfonso | 2 | 10/01/18 | 10/15/18 |
| Design PCB   * Collaborate with Dr. Stapleton | Mohamed | 2 | 10/01/18 | 10/16/18 |
| Design for MBED Interface   * High level drawings * Class, Use Case, Sequence and State Diagrams | Dylan | 4 | 10/01/18 | 10/31/18 |
| Order PCB to be printed   * Order 3 anticipating hardware failures | Mohamed | 2 | 10/16/18 | 11/01/18 |
| Updated Spec | Alfonso | 2 | 10/22/18 | 11/05/18 |
| Initial Website Layout   * Aesthetics (no code necessary) * Include buttons and functions | Dylan | 4 | 11/01/18 | 12/01/18 |
| Test Working PCB   * In lab with different inputs using power supply * Show results to Dr. Stapleton and get functional approval | Mohamed | 4 | 11/01/18 | 12/01/18 |
| Hardcopy Labor Cost Schedule | Alfonso | 2 | 11/05/18 | 11/19/18 |
| Draft Poster for Review   * Design made in Photoshop * Use of whitespace to save ink | Alfonso | 2 | 11/12/18 | 11/26/18 |
| Hardcopy Test Plan | Alfonso | 2 | 11/16/18 | 11/30/18 |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project Schedule – Spring 2019** | | | | |
| Signal reading interface for Mbed   * Define input and outputs of all selected Clicks * Create method for software to identify Click | Dylan | 4 | 01/16/19 | 02/16/19 |
| Test I/O with 10 Clicks   * Testing outputs in different environments | Mohamed | 4 | 01/16/19 | 02/16/19 |
| Design Website Skeleton   * HTML/CSS * Use Node JS or Bootstrap framework | Alfonso | 4 | 01/16/19 | 02/16/19 |
| Finalize MBED code   * Cleanup, debug and look for power optimizations | Dylan | 2 | 02/16/19 | 02/30/19 |
| Gather sample data for Clicks   * Using existing Mbed Code | Mohamed | 2 | 02/16/19 | 02/30/19 |
| Implement Website Functionality   * JavaScript * Tableau for graphs and statistical data | Alfonso | 4 | 02/16/19 | 03/16/19 |
| Full PCB and Clicks functionality test   * Compare with Functional Spec requirements | Mohamed | 5 | 03/01/19 | 04/16/19 |
| Full Mbed code functionality test   * Compare with Functional Spec requirements | Dylan | 5 | 03/01/19 | 04/16/19 |
| Full Website code functionality test   * Compare with Functional Spec requirements | Alfonso | 4 | 03/16/19 | 04/16/19 |
| Full functionality test   * Last chance to make sure all parts work together * Including debugging | Alfonso | 3 | 04/16/19 | 05/09/19 |
| Final Poster Review   * Review Poster to match final product | Dylan | 2 | 04/16/19 | 05/9/19 |
| Final Presentation Preparation   * PowerPoint creation * Planned rehearsals with team | Mohamed | 2 | 04/16/19 | 05/9/19 |
| Present on Senior Design Day | Alfonso | 1/7 | 05/10/19 | 05/10/19 |

# Sponsor Support Elements

Dylan Dean:

|  |  |  |
| --- | --- | --- |
| **Sponsor Support Elements** | | |
| **Element** | **First Needed** | **Needed Until** |
| Bi-Weekly meetings | 09/01/18 | 05/10/19 |
| Guided Visitation of NXP in Austin | TBD | TBD |
| Statement of Work Review and Signature | 09/19/18 | 09/24/18 |
| Technical Spec Review and Signature | 10/8/18 | 10/15/18 |
| Feedback on Poster and Product Display | 11/19/18 | 11/26/18 |
| Final Work Approval | 04/16/19 | 05/09/19 |

# Approvals

The signatures of the people below indicate an understanding in the purpose and content of this document by those signing it. By signing this document you indicate that you approve of the proposed project outlined in this Statement of Work and that the next steps may be taken to create a Functional Specification and proceed with the project.

|  |  |  |  |
| --- | --- | --- | --- |
| **Approver Name** | **Title** | **Signature** | **Date** |
| Alfonso de la Morena | Project Manager |  |  |
| Vanessa Yanez | D2 Project Manager |  |  |
| Dr. Stapleton | Faculty Sponsor |  |  |
| Dr. Kemp | Sponsor |  |  |
| Dr. Hinkle | Instructor |  |  |

**CHECKLIST for Statement of Work**

The Statement of Work is graded by your Lab Section Instructor. Grades are individual and NOT team.

Use this as a checklist before submitting your SOW. Comply with each item on this list to maximize your grade.

**Elements**:

1. **Title Page done correctly** □
   * Logos properly handled
2. **All instructions (red) deleted** □
3. **Written contributions of each team member clearly identified** □
4. **Table of Contents is correct**
   * Section numbers retained
   * Page numbers correct
   * No tries other than the 6 specified
5. **Executive Summary is clear and concise**
   * 1/2 to 3/4 of a page - no more
   * Outlines what you will produce
   * All bullet items on the template are addressed
6. **Business Need is short and concise**
   * Clearly states the value of this project
   * 1/2 a page or less
7. **Product Scope describes the product** (what you'll produce)

* **KEY:** You thoroughly researched what your project entails
* Key features and characteristics of what you'll design are listed
* A table or bulletized list is used to describe the features
* The performance is described
* How the product meets the business needs
* The section speaks only to what you'll produce
* Course documents are NOT listed
* You will have worked with your D2 Team, and your Sponsor and Faculty Sponsor

1. **Project Scope describes how you will do the project** □

* A table is used to describe the major tasks needed to finish the project
* They are scheduled in a way that makes sense
* Each task has a Duration, Start, and End Date
* The second semester is included
* You show when parts or software is ordered
* You show when a prototype will be ready for testing
* You show realization that the project must be done (ready to test) before the Characterization Report is due
* You will have worked with your D2 Team, and your Sponsor and Faculty Sponsor

1. **Sponsor Support Elements are complete and reasonable**

* You thought about what you'd need from the Sponsor and listed each item
* The items were general categories
  + Need specific microprocessor board - good
  + Need 10 ohm resistor - not good, too detailed
* It is clear to the Sponsor exactly what is expected of them

1. **All signatures were present before submitting the SOW** □
   * You worked with your Sponsor in a timely fashion
   * You gave them plenty of time to review the SOW
   * Signatures were written, i.e., not typed in