## Open Action Items
1.8 Official Click Sensor Hub Team Open Action Items
2018-12-05 | Last Update
Date | Description | DRI | Due By | #D | Notes / Comments
|  | Alfonso de la Morena |  | -
|  | Alfonso de la Morena |  | -
|  | Alfonso de la Morena |  | -
|  | Dylan Dean |  | -
|  | Dylan Dean |  | -
|  | Dylan Dean |  | -
|  | Mohamed Sghari |  | -
|  | Mohamed Sghari |  | -
|  | Mohamed Sghari |  | -
# items | Team Member
3 | Alfonso de la Morena
3 | Dylan Dean
3 | Mohamed Sghari
Note on B2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Closed Action Items
1.8 Official Click Sensor Hub Closed Action Items
2018-11-21 | Today's Date
Date | Description | DRI | Due By | #D | Notes / Comments
2018-09-11 | Set up SharePoint site. Organized necessary folders and uploaded relevant documents. | Alfonso de la Morena | 2018-09-12 |  | Closed 9/12/18
2018-09-11 | Gathered team suggestions into an easy to read format to present for our sponsors. | Dylan Dean | 2018-09-12 | - | Closed 9/12/18
2018-09-11 | Created document detailing important aspects of Hexiwear technology so team can understand limitations when speaking with sponsors. | Mohamed Sghari | 2018-09-12 | - | Closed 9/12/18
2018-09-17 | Set up Github and software for online meetings. | Alfonso de la Morena | 2018-09-24 | - | Closed 9/21/18
2018-09-17 | Outputting basic “Hello World” program on MBED compiler. | Dylan Dean | 2018-09-24 | - | Closed 9/21/18
2018-09-17 | Make a list of clicks that will be used for projects with reasoning. | Mohamed Sghari | 2018-09-24 | - | Closed 9/21/18
2018-09-10 | Finalize Statement of Work | Alfonso de la Morena | 2018-09-19 | - | Closed 9/21/18
2018-09-25 | Work on Hardcopy of Functional Spec | Alfonso de la Morena | 2018-10-15 | - | Closed 10/12/2018
2018-09-25 | Begin initial website design at very high level | Alfonso de la Morena | 2018-10-15 | - | Closed 10/12/2018
2018-09-25 | Work on Hardcopy of Functional Spec | Dylan Dean | 2018-10-15 | - | Closed 10/12/2018
2018-09-24 | Begin initial Mbed library design at very high level | Dylan Dean | 2018-10-15 | - | Closed 10/12/2018
2018-09-25 | Work on Hardcopy of Functional Spec | Mohamed Sghari | 2018-10-15 | - | Closed 10/12/2018
2018-09-24 | Begin Initial PCB Design complying with the mikroBUS standard | Mohamed Sghari | 2018-10-15 | - | Closed 10/12/2018
2018-10-10 | Practice IDR presentation and complete slides related to Deliverable #3. | Alfonso de la Morena | 2018-10-29 | - | Completed by 10/24/2018
2018-10-10 | Practice IDR presentation and complete slides related to Deliverable #2. | Dylan Dean | 2018-10-29 | - | Completed by 10/24/2018
2018-10-10 | Practice IDR presentation and complete slides related to Deliverable #1. | Mohamed Sghari | 2018-10-29 | - | Completed by 10/24/2018
2018-10-17 | Work on Hardcopy of Updated Functional Spec | Alfonso de la Morena | 2018-11-05 | - | Completed by 11/07/2018
2018-10-17 | Work on Hardcopy of Updated Functional Spec | Dylan Dean | 2018-11-05 | - | Completed by 11/07/2018
2018-10-17 | Work on Hardcopy of Updated Functional Spec | Mohamed Sghari | 2018-11-05 | - | Completed by 11/07/2018
2018-10-19 | Create study guide for Ethics Exam | Alfonso de la Morena | 2018-11-07 | - | Completed by 11/07/2018
2018-10-20 | Make list of parts to order and begin testing | Dylan Dean | 2018-11-15 | - | Completed by 11/07/2018
2018-11-05 | Work on Hardcopy of Labor Cost Schedule | Alfonso de la Morena | 2018-11-19 | - | Completed 11/19/2018
2018-11-05 | Work on Hardcopy of Labor Cost Schedule | Dylan Dean | 2018-11-19 | - | Completed 11/19/2018
2018-11-05 | Work on Hardcopy of Labor Cost Schedule | Mohamed Sghari | 2018-11-19 | - | Completed 11/19/2018
2018-11-05 | Print 11x7 Gantt Chart for Labor Cost Schedule | Alfonso de la Morena | 2018-11-19 | - | Closed 11/16/2018
2018-11-14 | Breadboard test 10 Clicks for interface functionality | Alfonso de la Morena | 2018-11-30 | - | Closed 12/5/2018
2018-11-14 | Work on Hardcopy of Test Plan | Alfonso de la Morena | 2018-11-30 | - | Closed 12/5/2018
2018-11-14 | Begin initial work on Website Skeleton writing basic HTML code | Alfonso de la Morena | 2018-11-30 | - | Closed 12/5/2018
2018-11-08 | Research Click Code for interfacing | Dylan Dean | 2018-11-26 | - | Closed 12/5/2018
2018-11-08 | Work on Poster Draft | Dylan Dean | 2018-11-26 | - | Closed 12/5/2018
2018-10-20 | Finalize EagleCAD PCB design and order first prototype | Mohamed Sghari | 2018-11-22 | - | Closed 12/5/2018
2018-11-08 | Meet with Dr Stapleton to discuss design choices and make corrections | Mohamed Sghari | 2018-11-22 | - | Closed 12/5/2018
# items | Team Member
10 | Alfonso de la Morena
8 | Dylan Dean
7 | Mohamed Sghari
Note on A2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Instructions and Lists
Team Members
Alfonso de la Morena
Dylan Dean
Mohamed Sghari
The DRI field uses the Data > Data Validation function in Excel, this allows you to quickly select the team members names. Change the names above to match your team.
If you copy and paste the last action item it will likely mess up the formulas below. Try inserting a row above then pasting the last row into the added row.
You can use the Data > Sort & Filter > Filter function on the row headings if you want to sort by DRI or due date. Same issue applies as above, have to be careful about adding rows below areas that are used in formulas.
Having column A blank makes it easier to capture a screenshot to paste in weekly. Also you can go into view and turn off gridlines if you want a cleaner look.