## Open Action Items
1.1 Official Project Name Open Action Items
2019-02-04 | Last Update
Date | Description | DRI | Due By | #D | Notes / Comments
2019-02-04 | Connect and utilize at least one Click Board on PCB | Alfonso de la Morena | 2019-02-16 | 12
2019-02-04 | Upload first version of user guide to website | Dylan Dean | 2019-02-16 | 12
2019-02-04 | Sauter Ics to PCB and do initial HW testing | Mohamed Sghari | 2019-02-16 | 12
# items | Team Member
1 | Alfonso de la Morena
1 | Dylan Dean
1 | Mohamed Sghari
Note on B2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Closed Action Items
1.1 Official Project Name Closed Action Items
2019-02-04 | Today's Date
Date | Description | DRI | Due By | #D | Notes / Comments
2019-01-16 | Finalize Parts and PCB Order | Alfonso de la Morena | 2019-02-04 | 0 | CLOSED: Parts ordered
2019-01-16 | Initial Website and User Guide Design | Dylan Dean | 2019-02-04 | 0 | CLOSED: Alpha version Finalized
2019-01-16 | Finalize PCB Design for ordering | Mohamed Sghari | 2019-02-04 | 0 | CLOSED: Design Finalized
# items | Team Member
1 | Alfonso de la Morena
1 | Dylan Dean
1 | Mohamed Sghari
Note on A2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Instructions and Lists
Team Members
Alfonso de la Morena
Dylan Dean
Mohamed Sghari
The DRI field uses the Data > Data Validation function in Excel, this allows you to quickly select the team members names. Change the names above to match your team.
If you copy and paste the last action item it will likely mess up the formulas below. Try inserting a row above then pasting the last row into the added row.
You can use the Data > Sort & Filter > Filter function on the row headings if you want to sort by DRI or due date. Same issue applies as above, have to be careful about adding rows below areas that are used in formulas.
Having column A blank makes it easier to capture a screenshot to paste in weekly. Also you can go into view and turn off gridlines if you want a cleaner look.