## Open Action Items
1.1 Official Project Name Open Action Items
2019-05-01 | Last Update
Date | Description | DRI | Due By | #D | Notes / Comments
2019-05-01 | Compile all software test results | Dylan Dean | 2019-05-06 | 5
2019-05-01 | Compile all hardware test results | Mohamed Sghari | 2019-05-06 | 5
2019-05-01 | Compile all project documents and results | Alfonso de la Morena | 2019-05-06 | 5
# items | Team Member
1 | Alfonso de la Morena
1 | Dylan Dean
1 | Mohamed Sghari
Note on B2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Closed Action Items
1.1 Official Project Name Closed Action Items
2019-05-01 | Today's Date
Date | Description | DRI | Due By | #D | Notes / Comments
2019-01-16 | Finalize Parts and PCB Order | Alfonso de la Morena | 2019-02-04 | - | CLOSED: Parts ordered
2019-01-16 | Initial Website and User Guide Design | Dylan Dean | 2019-02-04 | - | CLOSED: Alpha version finalized
2019-01-16 | Finalize PCB Design for ordering | Mohamed Sghari | 2019-02-04 | - | CLOSED: Design finalized
2019-02-04 | Excel Sheet of all 10 Click Connections for all 4 Socket Locations | Alfonso de la Morena | 2019-02-16 | - | CLOSED: File created
2019-02-04 | Create first version of user guide to website | Dylan Dean | 2019-02-16 | - | CLOSED: Document finished
2019-02-04 | Test programs on personal KL46Z-FRDM board | Mohamed Sghari | 2019-02-16 | - | CLOSED: Programs tested
2019-02-16 | State Diagrams for Progress Presentation | Alfonso de la Morena | 2019-02-25 | - | CLOSED: Diagrams created
2019-02-16 | Created social media for website links | Dylan Dean | 2019-02-25 | - | CLOSED: Youtube, Facebook created
2019-02-16 | Ordered missing resistor for board | Mohamed Sghari | 2019-02-25 | - | CLOSED: Part ordered
2019-02-16 | Additional solder and testing of second batch of boards purchased | Mohamed Sghari | 2019-03-11 | - | CLOSED: Board defects documented
2019-03-02 | Connect and utilize at least one Click Board on PCB | Alfonso de la Morena | 2019-03-02 | - | CLOSED: Bar Graph Click utilized
2019-03-02 | Write HTML, CSS and JavaScript Code necessary to put User Guide on Website | Dylan Dean | 2019-03-02 | - | CLOSED: Individual posts ready
2019-03-02 | Solder Ics to PCB and do initial HW testing | Mohamed Sghari | 2019-03-02 | - | CLOSED: Boards tested and documented
2019-03-04 | Code and test Temp2Hum Click | Alfonso de la Morena | 2019-03-11 | - | CLOSED: Board discontinued
2019-03-04 | Code and test Alcohol Click | Alfonso de la Morena | 2019-03-11 | - | CLOSED: Board not safe for KL46Z
2019-03-11 | Code and test Air Quality Click | Alfonso de la Morena | 2019-03-18 | - | CLOSED: Board test succesful
2019-03-11 | Code and test Bar Graph Click | Alfonso de la Morena | 2019-03-18 | - | CLOSED: Board test succesful
2019-03-27 | Finalize user guide | Dylan Dean | 2019-04-03 | - | CLOSED: User Guide finalized
2019-03-27 | Code and test Lightranger3 Click | Alfonso de la Morena | 2019-04-03 | - | CLOSED: LightRanger Working
2019-03-27 | Redesign board and order according to our findings on first board | Mohamed Sghari | 2019-04-03 | - | CLOSED: Board Redesigned
2019-03-27 | Complete Final Report | Alfonso de la Morena | 2019-04-17 | - | CLOSED: Sections finished
2019-04-03 | Code and test Gaussmeter Click | Alfonso de la Morena | 2019-04-10 | - | CLOSED: Gaussmeter code finished
2019-04-03 | Code and test Temp&Hum Click | Alfonso de la Morena | 2019-04-10 | - | CLOSED: Tem&Hum discontinued
2019-04-10 | Finish FDR Sections | Dylan Dean | 2019-04-17 | - | CLOSED: Sections finished
2019-04-10 | Finish FDR Sections | Mohamed Sghari | 2019-04-17 | - | CLOSED: Sections finished
2019-04-10 | Solder new boards | Mohamed Sghari | 2019-04-17 | - | CLOSED: Boards soldered
2019-04-17 | Finish FDR Sections | Alfonso de la Morena | 2019-04-24 | - | CLOSED: Sections finished
2019-04-17 | Complete Final Report | Dylan Dean | 2019-04-24 | - | CLOSED: Sections finished
2019-04-17 | Draft poster | Dylan Dean | 2019-04-24 | - | CLOSED: Poster drafted
2019-04-17 | Complete Final Report | Mohamed Sghari | 2019-04-24 | - | CLOSED: Sections finished
2019-04-17 | Test new boards | Mohamed Sghari | 2019-04-24 | - | CLOSED: Boards tested
2019-04-24 | Write Individual Report | Alfonso de la Morena | 2019-05-01 | - | CLOSED: Report finished
2019-04-24 | Prepare SDD code | Alfonso de la Morena | 2019-05-01 | - | CLOSED: Code tested
2019-04-24 | Write Individual Report | Dylan Dean | 2019-05-01 | - | CLOSED: Report finished
2019-04-24 | Prepare SSD presentation | Dylan Dean | 2019-05-01 | - | CLOSED: Presentation finished
2019-04-24 | Write Individual Report | Mohamed Sghari | 2019-05-01 | - | CLOSED: Report finished
2019-04-24 | Test SDD board | Mohamed Sghari | 2019-05-01 | - | CLOSED: Boards tested
# items | Team Member
15 | Alfonso de la Morena
10 | Dylan Dean
12 | Mohamed Sghari
Note on A2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.

## Instructions and Lists
Team Members
Alfonso de la Morena
Dylan Dean
Mohamed Sghari
The DRI field uses the Data > Data Validation function in Excel, this allows you to quickly select the team members names. Change the names above to match your team.
If you copy and paste the last action item it will likely mess up the formulas below. Try inserting a row above then pasting the last row into the added row.
You can use the Data > Sort & Filter > Filter function on the row headings if you want to sort by DRI or due date. Same issue applies as above, have to be careful about adding rows below areas that are used in formulas.
Having column A blank makes it easier to capture a screenshot to paste in weekly. Also you can go into view and turn off gridlines if you want a cleaner look.