## F'18
1.8 Official Click Sensor Hub Team Milestone Schedule
2018-11-21 | Last Update
71 | calendar days until Senior Design Day
DRI | Task | Dur | Start | End | Status
Alfonso | Set up SharePoint site. Organized necessary folders and uploaded relevant documents. | 2 | 2018-09-10 | 2018-09-12 | Completed
Dylan | Gathered team suggestions into an easy to read format to present for our sponsors. | 2 | 2018-09-10 | 2018-09-12 | Completed
Mohamed | Created document detailing important aspects of Hexiwear technology so team can understand limitations when speaking with sponsors. | 2 | 2018-09-10 | 2018-09-12 | Completed
Alfonso | Set up Github and software for online meetings. | 5 | 2018-09-12 | 2018-09-17 | Completed
Dylan | Outputting basic “Hello World” program on MBED compiler . | 5 | 2018-09-12 | 2018-09-17 | Completed
Mohamed | Make a list of clicks that will be used for projects with reasoning. | 5 | 2018-09-12 | 2018-09-17 | Completed
Alfonso | Coordinate Hardcopy of Statement of Work | 14 | 2018-09-10 | 2018-09-24 | Completed
Mohamed | Begin Initial PCB Design complying with the mikroBUS standard | 6 | 2018-09-24 | 2018-09-30 | Completed
Dylan | Begin initial Mbed library design at very high level | 6 | 2018-09-24 | 2018-09-30 | Completed
Alfonso | Coordinate Hardcopy of Functional Spec | 20 | 2018-09-25 | 2018-10-15 | Completed
Mohamed | Initial Design PCB Finalized | 17 | 2018-10-15 | 2018-11-01 | Completed
Dylan | Initial Design for MBED Interface Finalized | 17 | 2018-10-15 | 2018-11-01 | Completed
Alfonso | Coordinate Initial Design Review Presentation | 8 | 2018-10-15 | 2018-10-23 | Completed
Alfonso | Coordinate Hardcopy Updated Spec | 14 | 2018-10-22 | 2018-11-05 | Completed
Mohamed | Order PCB to be printed | 26 | 2018-10-20 | 2018-11-15 | In progress
Alfonso | Design for Initial Website Layout | 30 | 2018-11-01 | 2018-12-01 | In progress
Alfonso | Coordinate Hardcopy of Labor Cost Schedule | 14 | 2018-11-05 | 2018-11-19 | In progress
Mohamed | Testing PCB | 16 | 2018-11-15 | 2018-12-01 | Late
Mohamed | First Draft of Poster for Review | 14 | 2018-11-12 | 2018-11-26 | In progress
Alfonso | Coordinate Hardcopy of Test Plan | 14 | 2018-11-16 | 2018-11-30 | Not Started
Alfonso | Second Design-Manufacturing Cycle for PCB | 45 | 2018-12-01 | 2019-01-15 | Not Started
| Winter Break | 39 | 2018-12-14 | 2019-01-22
Dylan | Complete Signal reading library with interface class using Mbed | 31 | 2019-01-16 | 2019-02-16 | In progress
Mohamed | Full functionality test of I/O with 10 Clicks on functioning PCB | 31 | 2019-01-16 | 2019-02-16 | In progress
Alfonso | Initial Desing for Website with HTML and CSS | 31 | 2019-01-16 | 2019-02-16 | In progress
Dylan | Optimize Mbed code and test with all Clicks | 14 | 2019-02-16 | 2019-03-02 | Not Started
Mohamed | Gather sample data from Clicks | 14 | 2019-02-16 | 2019-03-02 | Not Started
Alfonso | Implement Website Functionality | 28 | 2019-02-16 | 2019-03-16 | Not Started
Alfonso | Progress Presentations | 2 | 2019-02-25 | 2019-02-27 | Not Started
Mohamed | Full PCB and Clicks functionality test | 44 | 2019-03-03 | 2019-04-16 | Not Started
Dylan | Full Mbed code functionality test | 44 | 2019-03-03 | 2019-04-16 | Not Started
Alfonso | Project Demos | 2 | 2019-03-11 | 2019-03-13 | Not Started
Alfonso | Full Website code functionality test | 31 | 2019-03-16 | 2019-04-16 | Not Started
Alfonso | Final Design Review | 2 | 2019-04-15 | 2019-04-17 | Not Started
Alfonso | Full Project functionality test | 22 | 2019-04-17 | 2019-05-09 | Not Started
Mohamed | Final Poster Review | 22 | 2019-04-17 | 2019-05-09 | Not Started
Dylan | Final Presentation Preparation | 22 | 2019-04-17 | 2019-05-09 | Not Started
Alfonso | Senior Design Day | 0 | 2019-05-07 | 2019-05-07 | Not Started
Alfonso | Post descriptions reports and source code in Mbed and NXP community forums | 6 | 2019-05-11 | 2019-05-17 | Not Started
Note on B2: Hinkle, Lee B: To automatically add todays date hold down <cntrl> press = key then ; key. This will enter a static date that won't change. If you use =TODAY(); it will update automatically.
Note on B4: Hinkle, Lee B: Designated Responsible Individual. Put the name of the team member responsible for the task here. If more then one, pick the lead person (or better yet divide the task further into individual tasks)
Note on C4: Hinkle, Lee B: Briefly describe the deliverable the DRI must provide back to the team. GOOD: Power Budget & Battery Recommendation BAD: Investigate Battery Technologies

## Fields
Status
Not Started
In progress
Late
Completed
Overdue
Critical