## Fall 2018
Click Sensor Hub
Sponsor: NXP Semiconductors
Project Manager: Alfonso de la Morena |  | Project Start: | 2018-09-07
Team Members: Dylan Dean, Mohamed Sghari |  | Display Week: | 1 |  |  | 2018-09-07 | [6 empty] | 2018-09-14 | [6 empty] | 2018-09-21 | [6 empty] | 2018-09-28 | [6 empty] | 2018-10-05 | [6 empty] | 2018-10-12 | [6 empty] | 2018-10-19 | [6 empty] | 2018-10-26 | [6 empty] | 2018-11-02 | [6 empty] | 2018-11-09 | [6 empty] | 2018-11-16 | [6 empty] | 2018-11-23 | [6 empty] | 2018-11-30 | [6 empty] | 2018-12-07 | [6 empty] | 2018-12-14 | [6 empty] | 2018-12-21 | [6 empty] | 2018-12-28
 | time axis 2018-09-07 to 2019-01-03
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2018-09-07 to 2019-01-03
Fall 2018 Deliverables |  | 100% | 2018-09-10 | 2019-01-22 | 135
Set up SharePoint site. Organized necessary folders and uploaded relevant documents. | Alfonso | 100% | 2018-09-10 | 2018-09-12 | 3 | bar: 2018-09-18
Gathered team suggestions into an easy to read format to present for our sponsors. | Dylan | 100% | 2018-09-12 | 2018-09-17
Listed Sponsor Concerns in one concise document to discuss in meeting. | Mohamed | 100% | 2018-09-12 | 2018-09-17
Set up Github and software for online meetings. | Alfonso | 100% | 2018-09-12 | 2018-09-17
Outputting basic “Hello World” program on MBED compiler . | Dylan | 100% | 2018-09-12 | 2018-09-17
Make a list of clicks that will be used for projects with reasoning. | Mohamed | 100% | 2018-09-12 | 2018-09-17
Coordinate Hardcopy of Statement of Work | Alfonso | 100% | 2018-09-10 | 2018-09-24
Begin Initial PCB Design complying with the mikroBUS standard | Mohamed | 100% | 2018-09-24 | 2018-09-30
Begin initial Mbed library design at very high level | Dylan | 100% | 2018-09-24 | 2018-09-30
Coordinate Hardcopy of Functional Spec | Alfonso | 100% | 2018-09-25 | 2018-10-15 | 21
Initial Design PCB Finalized | Mohamed | 100% | 2018-10-15 | 2018-11-01 | 18
Initial Design for MBED Interface Finalized | Dylan | 100% | 2018-10-15 | 2018-11-01
Coordinate Initial Design Review Presentation | Alfonso | 100% | 2018-10-15 | 2018-10-23
Coordinate Hardcopy Updated Spec | Alfonso | 100% | 2018-10-22 | 2018-11-05
Order PCB to be printed | Mohamed | 100% | 2018-10-20 | 2018-11-15
Design for Initial Website Layout | Alfonso | 100% | 2018-11-01 | 2018-12-01
Coordinate Hardcopy of Labor Cost Schedule | Alfonso | 100% | 2018-11-05 | 2018-11-19
Testing PCB | Mohamed | 100% | 2018-11-15 | 2018-12-01
First Draft of Poster for Review | Mohamed | 100% | 2018-11-12 | 2018-11-26 | 15
Coordinate Hardcopy of Test Plan | Alfonso | 100% | 2018-11-16 | 2018-11-30
Second Design-Manufacturing Cycle for PCB | Alfonso | 100% | 2018-12-01 | 2019-01-15
Winter Break | Team | 100% | 2018-12-14 | 2019-01-22 | 40
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Spring 2019
Click Sensor Hub
Sponsor: NXP Semiconductors
Project Manager: Alfonso de la Morena |  | Project Start: | 2019-01-12
Team Members: Dylan Dean, Mohamed Sghari |  | Display Week: | 1 |  |  | 2019-01-12 | [6 empty] | 2019-01-18 | [6 empty] | 2019-01-25 | [6 empty] | 2019-02-01 | [6 empty] | 2019-02-08 | [6 empty] | 2019-02-15 | [6 empty] | 2019-02-22 | [6 empty] | 2019-03-01 | [6 empty] | 2019-03-08 | [6 empty] | 2019-03-15 | [6 empty] | 2019-03-22 | [6 empty] | 2019-03-29 | [6 empty] | 2019-04-05 | [6 empty] | 2019-04-12 | [6 empty] | 2019-04-19 | [6 empty] | 2019-04-26 | [6 empty] | 2019-05-03
 | time axis 2019-01-11 to 2019-05-09
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2019-01-11 to 2019-05-09
Spring 2019 Deliverables |  | 100% | 2019-01-16 | 2019-05-20 | 125
Complete Signal reading library with interface class using Mbed | Dylan | 100% | 2019-01-16 | 2019-02-16 | 32
Full functionality test of I/O with 10 Clicks on functioning PCB | Mohamed | 100% | 2019-01-16 | 2019-02-16
Initial Desing for Website with HTML and CSS | Alfonso | 100% | 2019-01-16 | 2019-02-16
Optimize Mbed code and test with all Clicks | Dylan | 100% | 2019-02-16 | 2019-03-29
Gather sample data from Clicks | Mohamed | 100% | 2019-02-16 | 2019-03-29
Implement Website Functionality | Alfonso | 100% | 2019-02-16 | 2019-03-29
Full PCB and Clicks functionality test | Mohamed | 100% | 2019-03-03 | 2019-04-16
Full Mbed code functionality test | Dylan | 100% | 2019-03-03 | 2019-04-16
Full Website code functionality test | Alfonso | 100% | 2019-03-16 | 2019-04-16
Full Project functionality test | Alfonso | 100% | 2019-04-17 | 2019-05-04 | 18
Final Poster Review | Mohamed | 100% | 2019-04-17 | 2019-05-04 | 18
Final Presentation Preparation | Dylan | 100% | 2019-04-17 | 2019-05-04
Senior Design Day | Team | 100% | 2019-05-05 | 2019-05-05
Post descriptions reports and source code in Mbed and NXP community forums | Alfonso | 100% | 2019-05-06 | 2019-05-09
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.