## ProjectSchedule
HexiMed
Sponsor: NXP Semiconductors
Project Manager: Vanessa Yanez |  | Project Start: | 2018-01-19
Team Members: Franco Justo, Kelly Carranza |  | Display Week: | 1 |  |  | 2018-01-19 | [6 empty] | 2018-01-26 | [6 empty] | 2018-02-02 | [6 empty] | 2018-02-09 | [6 empty] | 2018-02-16 | [6 empty] | 2018-02-23 | [6 empty] | 2018-03-02 | [6 empty] | 2018-03-09 | [6 empty] | 2018-03-16 | [6 empty] | 2018-03-23 | [6 empty] | 2018-03-30 | [6 empty] | 2018-04-06 | [6 empty] | 2018-04-13 | [6 empty] | 2018-04-20 | [6 empty] | 2018-04-27 | [6 empty] | 2018-05-04 | [6 empty] | 2018-05-11
 | time axis 2018-01-19 to 2018-05-17
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2018-01-19 to 2018-05-17
Initial Design Research |  | 100% | 2018-01-19 | 2018-02-12 | 25
Research Hexiwear | Team | 100% | 2018-01-19 | 2018-01-26 | 8
Research Clickboards | Team | 100% | 2018-01-19 | 2018-01-26 | 8
Construct Prototype | Team | 100% | 2018-01-29 | 2018-02-05 | 8
Outline Design Plan | Team | 100% | 2018-02-05 | 2018-02-12 | 8
Acquire Components | Team | 100% | 2018-02-14 | 2018-04-04 | 50
Spring 2018 Deliverables |  | 50% | 2018-01-22 | 2018-05-03 | 102
Statement of Work | Team | 100% | 2018-01-22 | 2018-02-12 | 22
Functional Specification | Team | 100% | 2018-02-14 | 2018-03-05 | 20
Initial Design Review | Team | 100% | 2018-02-28 | 2018-03-21 | 22
Labor Cost Schedule | Team | 100% | 2018-03-28 | 2018-04-11 | 15
Poster Draft | Team | 0% | 2018-04-04 | 2018-04-25 | 22
Test Plan | Team | 0% | 2018-04-04 | 2018-04-30
Inidividual Reports | Team | 0% | 2018-04-04 | 2018-05-02 | 29
Poster PDF Final | Team | 0% | 2018-04-04 | 2018-05-03 | 30
Prototype Development |  | 0% | 2018-04-04 | 2018-05-10 | 37
Program, Test, and Debug NFC Click/Tags | Vanessa | 0% | 2018-04-04 | 2018-05-10 | 37
Program, Test, and Debug User Input | Franco | 0% | 2018-04-04 | 2018-05-10 | 37
Program, Test, and Debug Audio alarm | Kelly | 0% | 2018-04-04 | 2018-05-10 | 37
Senior Design Day |  | 0% | 2018-05-01 | 2018-05-10 | 10
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.