## Fall 2018
LABOR ESTIMATE FALL 2018
| Des Engr | Test Engr | Tech Writer | CAD Drafter | Administrator | Manager | Consultant | TOTAL
Burdened Hourly Rate | 77.37 | 61.5 | 42.85 | 40.3 | 30.17 | 101.65 | 72.76
Task | Hours Required
Set up SharePoint site. Organized necessary folders and uploaded relevant documents. | [5 empty] | 3 |  | 304.95
Gathered team suggestions into an easy to read format to present for our sponsors. | [5 empty] | 3 |  | 304.95
Listed Sponsor Concerns in one concise document to discuss in meeting. | [5 empty] | 3 |  | 304.95
Set up Github and software for online meetings. | 2 |  |  |  |  | 3 |  | 459.69
Outputting basic “Hello World” program on MBED compiler . | 4 | 2 | [5 empty] | 432.48
Make a list of clicks that will be used for projects with reasoning. |  | 10 |  |  |  |  | 2 | 760.52
Coordinate Hardcopy of Statement of Work |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Begin Initial PCB Design complying with the mikroBUS standard | 40 | [6 empty] | 3094.8
Begin initial Mbed library design at very high level | 20 | [6 empty] | 1547.4
Coordinate Hardcopy of Functional Spec |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Initial Design PCB Finalized | 40 |  |  | 40 |  |  |  | 4706.8
Initial Design for MBED Interface Finalized | 40 | [6 empty] | 3094.8
Coordinate Initial Design Review Presentation |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Coordinate Hardcopy Updated Spec |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Order PCB to be printed |  |  |  |  | 4 | 4 |  | 527.28
Design for Initial Website Layout | 40 | [6 empty] | 3094.8
Coordinate Hardcopy of Labor Cost Schedule |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Testing PCB |  | 40 | [5 empty] | 2460
First Draft of Poster for Review | 10 | [6 empty] | 773.7
Coordinate Hardcopy of Test Plan |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Second Design-Manufacturing Cycle for PCB | 40 |  |  | 40 |  |  |  | 4706.8
Total Burdened Cost | 18259.32 | 3198 | 10284 | 3224 | 3741.08 | 26022.4 | 1455.2 | 66184

## Fall 2018 (2)
LABOR ESTIMATE FALL 2018
| Des Engr | Test Engr | Tech Writer | CAD Drafter | Administrator | Manager | Consultant | TOTAL
Burdened Hourly Rate | 77.37 | 61.5 | 42.85 | 40.3 | 30.17 | 101.65 | 72.76
Task | Hours Required
Set up Github and software for online meetings. | 2 |  |  |  |  | 3 |  | 459.69
Outputting basic “Hello World” program on MBED compiler . | 4 | 2 | [5 empty] | 432.48
Make a list of clicks that will be used for projects with reasoning. |  | 10 |  |  |  |  | 2 | 760.52
Coordinate Hardcopy of Statement of Work |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Begin Initial PCB Design complying with the mikroBUS standard | 40 | [6 empty] | 3094.8
Begin initial Mbed library design at very high level | 20 | [6 empty] | 1547.4
Coordinate Hardcopy of Functional Spec |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Initial Design PCB Finalized | 40 |  |  | 40 |  |  |  | 4706.8
Initial Design for MBED Interface Finalized | 40 | [6 empty] | 3094.8
Coordinate Initial Design Review Presentation |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Coordinate Hardcopy Updated Spec |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Design for Initial Website Layout | 40 | [6 empty] | 3094.8
Coordinate Hardcopy of Labor Cost Schedule |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Testing PCB |  | 40 | [5 empty] | 2460
First Draft of Poster for Review | 10 | [6 empty] | 773.7
Coordinate Hardcopy of Test Plan |  |  | 40 |  | 20 | 40 | 3 | 6601.68
Second Design-Manufacturing Cycle for PCB | 40 |  |  | 40 |  |  |  | 4706.8
Total Burdened Cost | 18259.32 | 3198 | 10284 | 3224 | 3620.4 | 24700.95 | 1455.2 | 64741.87

## Spring 2019
LABOR ESTIMATE SPRING 2019
| Des Engr | Test Engr | Tech Writer | CAD Drafter | Administrator | Manager | Consultant | TOTAL
Burdened Hourly Rate | 77.37 | 61.5 | 42.85 | 40.3 | 30.17 | 101.65 | 72.76
Task | Hours Required
Complete Signal reading library with interface class using Mbed | 40 | [6 empty] | 3094.8
Full functionality test of I/O with 10 Clicks on functioning PCB |  | 40 | [5 empty] | 2460
Initial Desing for Website with HTML and CSS | 40 | [6 empty] | 3094.8
Optimize Mbed code and test with all Clicks | 40 | [6 empty] | 3094.8
Gather sample data from Clicks |  | 40 | [5 empty] | 2460
Implement Website Functionality | 40 | [6 empty] | 3094.8
Full PCB and Clicks functionality test | 20 | 80 | [5 empty] | 6467.4
Full Mbed code functionality test | 20 | 80 | [5 empty] | 6467.4
Full Website code functionality test | 20 | 80 | [5 empty] | 6467.4
Full Project functionality test | 20 | 80 | [5 empty] | 6467.4
Final Poster Review |  |  |  |  | 10 | 20 |  | 2334.7
Final Presentation Preparation |  |  |  |  | 10 | 20 |  | 2334.7
Senior Design Day | 5 | 5 |  |  | 5 | 5 | 5 | 1717.25
Post descriptions reports and source code in Mbed and NXP community forums | [5 empty] | 10 |  | 1016.5
Total Burdened Cost | 18955.65 | 24907.5 | 0 | 0 | 754.25 | 5590.75 | 363.8 | 50571.95

## TOTAL
116755.95
445.58